## BOTFORCE RPA IDE
Commit Date | Code Owner | Feature(s) | Commit Status | JIRA no. | Reviewer | Repo Name | Reviewer Comments
17 dec'18 | Ram.P | Bug Fixes - Open Page & Launch Browser; | done |  | GP | botforce-IDE Development
17 dec'18 | Srinu | Enter Keystrokes - 'To image' feature. | done |  | GP | botforce-IDE Development
17 dec'18 | GP | Add getCell action, Add write cell action. | done |  | GP | botforce-IDE Development
17 dec'18 | Akhil | Bug Fixes for SFTP & .CSV; | done |  | GP | botforce-IDE Development
17 dec'18 | Sravya | Cognitive Feature; Single actions changes - DOM, Snap, Read, Wait, Enter Keystrokes; Main Folder Changes. | done |  | GP | botforce-IDE Development
17 dec'18 | Manoj | Jump Statement action - changes/modifications | done |  | GP | botforce-IDE Development
18 dec'18 | Harisha | MS OUTLOOK actions - GET Mail data into Dynamic Variable; | done |  | GP | botforce-IDE Development
18 dec'18 | Ram.P |  | No Commit |  | GP | botforce-IDE Development
18 dec'18 | Srinu |  | No Commit |  | GP | botforce-IDE Development
18 dec'18 | GP |  | No Commit |  | GP | botforce-IDE Development
18 dec'18 | Akhil |  | No Commit |  | GP | botforce-IDE Development
18 dec'18 | Sravya | CSS changes for 'HTTP API & UI Automation' action items | done(Waiting for Code MERGE) |  | GP | botforce-IDE Development
18 dec'18 | Manoj |  | No Commit |  | GP | botforce-IDE Development
19 Dec'18 | Harisha |  | No Commit |  |  | botforce-IDE Development
19 Dec'18 | Ram.P |  | No Commit |  |  | botforce-IDE Development
19 Dec'18 | Srinu | Bug Fixes in 'Mouse Location Selector 'action, Open Page action in 'For-in' loop & 'IF-Else'. | done | BRID-58,BRID-59; BRID-63 |  | botforce-IDE Development
19 Dec'18 | GP |  | No Commit |  |  | botforce-IDE Development
19 Dec'18 | Akhil |  | No Commit |  |  | botforce-IDE Development
19 Dec'18 | Sravya |  | No Commit |  |  | botforce-IDE Development
19 Dec'18 | Manoj |  | No Commit |  |  | botforce-IDE Development
24 Dec'18 | Harisha | outlook "send mail" feature. | done | BRID-85 |  | botforce-IDE Development
24 Dec'18 | Ram.P | n/a | No Commit |  |  | botforce-IDE Development
24 Dec'18 | Srinu | Bug fixes - Record & Play & Conditions - Excel integration. | No Commit | BRID-84; BRID-65 |  | botforce-IDE Development
24 Dec'18 | GP | n/a | No Commit |  |  | botforce-IDE Development
24 Dec'18 | Sravya | n/a | No Commit |  |  | botforce-IDE Development
24 Dec'18 | Madhuri | Orchestrator | No Commit |  |  | botforce-IDE Development
26 Dec'18 | Harisha | Outlook Code merge issues fix; Outlook Mail Configuration | done | BRID-86; BRID-87 |  | botforce-IDE Development
26 Dec'18 | Ram.P | OCR Changes | No Commit |  |  | botforce-IDE Development
26 Dec'18 | Srinu | bug fixes & Excel actions | No Commit |  |  | botforce-IDE Development
26 Dec'18 | GP | testing packaging scripts | No Commit |  |  | botforce-IDE Development
26 Dec'18 | Sravya | Check' Action item | WIP |  |  | botforce-IDE Development
27 Dec'18 | Harisha | Bug fixes & Merge issues in OUTLOOK; Outlook Mail Configuration; | done | BRID-87; BRID-85 |  | botforce-IDE Development
27 Dec'18 | Sinivas Ravuri | Bug fix in 'Excel' actions in 'if' condition; Record & Play - display for user when recording started; | done | BRID-84; BRID-65 |  | botforce-IDE Development
28th Dec'18 | Harisha | Bug fixes & Merge issues in OUTLOOK; Outlook Mail Configuration; added outlook in inner loops and inner if added outlook config functionality; outlook config with appId and passwords; | done | BRID-87 |  | botforce-IDE Development
31st Dec'18 | Sravya | CHECK' Action item; 'COUNT' Action item into 'IF-Else'; | done | BRID-88;BRID-89 |  | botforce-IDE Development